## Model
Burndown Chart Template
Day | Start | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Estimated % Remaining | 100 | 96.6667 | 93.3333 | 90 | 86.6667 | 83.3333 | 80 | 76.6667 | 73.3333 | 70 | 66.6667 | 63.3333 | 60 | 56.6667 | 53.3333 | 50 | 46.6667 | 43.3333 | 40 | 36.6667 | 33.3333 | 30 | 26.6667 | 23.3333 | 20 | 16.6667 | 13.3333 | 10 | 6.6667 | 3.3333 | 2.7534e-14
CHG |  | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333
Actual % Remaining | 100 | 96.6667 | 93.3333 | 90 | 86.6667 | 83.3333 | 80 | 76.6667 | 73.3333 | 70 | 66.6667 | 63.3333 | 60 | 56.6667 | 53.3333 | 50 | 46.6667 | 43.3333 | 40 | 36.6667 | 33.3333 | 30 | 26.6667 | 23.3333 | 20 | 16.6667 | 13.3333 | 10 | 6.6667 | 3.3333 | 0
Estimated Work Effort | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450
CHG |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Actual Work Effort | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450
This example model uses a 30 day sprint. Below, you can define the total capacity of your team and how much estimated completion and work effort is accomplished each day. Using the cream colored cells above, replace the calculated cells with your actual burndown information.
Estimated % Complete Per Day |  | 3: 3.3333
Total Capacity |  | 3: 450
Total Work Per Day |  | 3: 15

## Curved Model
Burndown Chart Template
Day | Start | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Estimated % Remaining | 100 | 99 | 99 | 99 | 99 | 98 | 97 | 96 | 94 | 92 | 90 | 87 | 84 | 81 | 77 | 73 | 69 | 64 | 59 | 54 | 48 | 42 | 36 | 29 | 22 | 15 | 9 | 4 | 0 | 0 | 0
CHG |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 6 | 5 | 4 | 0 | 0
Actual % Remaining | 100 | 100 | 100 | 100 | 100 | 99 | 98 | 97 | 95 | 93 | 91 | 88 | 85 | 82 | 78 | 74 | 70 | 65 | 60 | 55 | 49 | 43 | 37 | 30 | 23 | 16 | 10 | 5 | 1 | 1 | 0
Estimated Work Effort | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450
CHG |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Actual Work Effort | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450
This example model uses a 30 day sprint, showing a curved model for the amount of progress in completion of features.
Estimated % Complete Per Day |  | 3: 3.3333
Total Capacity |  | 3: 450
Total Work Per Day |  | 3: 15

## Good Burndown
Burndown Chart Template
Day | Start | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Estimated % Remaining | 100 | 96.6667 | 93.3333 | 90 | 86.6667 | 83.3333 | 80 | 76.6667 | 73.3333 | 70 | 66.6667 | 63.3333 | 60 | 56.6667 | 53.3333 | 50 | 46.6667 | 43.3333 | 40 | 36.6667 | 33.3333 | 30 | 26.6667 | 23.3333 | 20 | 16.6667 | 13.3333 | 10 | 6.6667 | 3.3333 | 2.7534e-14
CHG |  | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 10 | 10 | 10 | 5 | 0 | 0 | 0 | 5 | 0 | -10 | 5 | 5 | 5 | 5 | 10 | 10 | 5 | 0 | 0 | 0 | 5 | 0 | 0
Actual % Remaining | 100 | 100 | 100 | 100 | 95 | 90 | 85 | 80 | 70 | 60 | 50 | 45 | 45 | 45 | 45 | 40 | 40 | 50 | 45 | 40 | 35 | 30 | 20 | 10 | 5 | 5 | 5 | 5 | 0 | 0 | 0
Estimated Work Effort | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450
CHG |  | 10 | 12 | 15 | 17 | 12 | 15 | 15 | 12 | 16 | 17 | 15 | 10 | 10 | 5 | 5 | 20 | 30 | 10 | 15 | 10 | 7 | 5 | 8 | 9 | 7 | 6 | 9 | 8 | 7 | 6
Actual Work Effort | 0 | 10 | 22 | 37 | 54 | 66 | 81 | 96 | 108 | 124 | 141 | 156 | 166 | 176 | 181 | 186 | 206 | 236 | 246 | 261 | 271 | 278 | 283 | 291 | 300 | 307 | 313 | 322 | 330 | 337 | 343
This example model shows a good burndown where the work effort is below the estimate and features are completed before the end of the sprint.
Estimated % Complete Per Day |  | 3: 3.3333
Total Capacity |  | 3: 450
Total Work Per Day |  | 3: 15

## Bad Burndown
Burndown Chart Template
Day | Start | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Estimated % Remaining | 100 | 96.6667 | 93.3333 | 90 | 86.6667 | 83.3333 | 80 | 76.6667 | 73.3333 | 70 | 66.6667 | 63.3333 | 60 | 56.6667 | 53.3333 | 50 | 46.6667 | 43.3333 | 40 | 36.6667 | 33.3333 | 30 | 26.6667 | 23.3333 | 20 | 16.6667 | 13.3333 | 10 | 6.6667 | 3.3333 | 2.7534e-14
CHG |  | 0 | 0 | 0 | 5 | 3 | 5 | 4 | 6 | 2 | 3 | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 3 | 1 | 5 | 10 | 5 | 0 | 5
Actual % Remaining | 100 | 100 | 100 | 100 | 95 | 92 | 87 | 83 | 77 | 75 | 72 | 66 | 63 | 61 | 60 | 60 | 60 | 60 | 60 | 60 | 58 | 56 | 55 | 53 | 50 | 49 | 44 | 34 | 29 | 29 | 24
Estimated Work Effort | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 390 | 405 | 420 | 435 | 450
CHG |  | 10 | 12 | 11 | 13 | 14 | 13 | 12 | 11 | 10 | 9 | 12 | 23 | 12 | 18 | 13 | 16 | 25 | 21 | 25 | 23 | 18 | 17 | 15 | 13 | 15 | 20 | 25 | 20 | 30 | 15
Actual Work Effort | 0 | 10 | 22 | 33 | 46 | 60 | 73 | 85 | 96 | 106 | 115 | 127 | 150 | 162 | 180 | 193 | 209 | 234 | 255 | 280 | 303 | 321 | 338 | 353 | 366 | 381 | 401 | 426 | 446 | 476 | 491
This example model shows a bad burndown where the work effort exceeds the estimate and features aren't completed at the end of the sprint.
Estimated % Complete Per Day |  | 3: 3.3333
Total Capacity |  | 3: 450
Total Work Per Day |  | 3: 15